## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Geetha | 2026-08-23 | Document parsing failed to handle different text extraction behavior consistently across supported file types. | Sprint 1 | Geetha | Logical | Added file-type-specific extraction and normalized the extracted text. | 2026-08-24 | Closed | Verified with supported PDF, DOCX, TXT and CSV samples.
2 | Geetha | 2026-08-29 | Ambiguous queries were entering the normal retrieval path without enough context. | Sprint 2 | Geetha | Logical | Added query classification and routing for ambiguous requests. | 2026-08-30 | Closed | Handled through the Query Understanding Agent.
3 | Geetha | 2026-09-01 | Low-relevance retrieved chunks could still be passed to response generation. | Sprint 2 | Geetha | Logical | Added relevance filtering before grounded response generation. | 2026-09-02 | Closed | Unsupported evidence is no longer treated as valid context.
4 | Geetha | 2026-09-05 | Follow-up questions did not consistently retain the previous turn's context. | Sprint 3 | Geetha | Logical | Added conversation-memory handling to preserve recent turns. | 2026-09-07 | Closed | Validated with multi-turn question sequences.
5 | Geetha | 2026-09-09 | Voice input depended on browser permission and recognition availability. | Sprint 3 | Geetha | User Interface | Added permission handling and a text-input fallback. | 2026-09-10 | Closed | Fallback is available when speech recognition is unavailable.
6 | Geetha | 2026-09-22 | Analytics records did not initially capture enough information to identify knowledge gaps. | Sprint 4 | Geetha | Maintainability | Standardized query type, confidence, retrieval and resolution fields. | 2026-09-24 | Closed | Supports unanswered and low-confidence analysis.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others